## Book2
TaskID | ProjectID | ProjectDiscipline | Status | Description | Location | Created | Target | Actual | Delay | Priority | Overdue | RootCause | Risk | Hours | Comments
T-1015 | PRJ001 | PRJ-STR | Closed | Column Installation | Grid A5 | 2024-02-01 | 2024-02-05 | 2024-02-07 | 2 | High | TRUE | Crane Breakdown | High | 56 | Repaired after 1 day
T-1016 | PRJ001 | PRJ-INT | Open | Paint Finishes | Lobby | 2024-05-10 | 2024-05-20 |  |  | Medium | FALSE |  | Medium | 38 | Awaiting color approval
T-1017 | PRJ001 | PRJ-MEP | Closed | HVAC Ductwork | Mechanical | 2024-03-15 | 2024-03-22 | 2024-03-18 | -4 | Medium | FALSE |  | Low | 72 | Ahead of schedule
T-1018 | PRJ001 | PRJ-ARC | Closed | Curtain Wall Install | South Facade | 2024-04-01 | 2024-04-15 | 2024-04-20 | 5 | High | TRUE | Design Revision | High | 120 | Required engineering sign-off
T-1019 | PRJ001 | PRJ-SITE | Closed | Underground Utilities | West Yard | 2024-01-10 | 2024-01-25 | 2024-02-05 | 11 | High | TRUE | Weather Delay | Medium | 90 | Heavy rains for 1 week
T-1020 | PRJ001 | PRJ-STR | Closed | Deck Pour | Level 3 | 2024-03-05 | 2024-03-08 | 2024-03-08 |  | High | FALSE |  | High | 64 | Perfect weather conditions
T-1021 | PRJ001 | PRJ-INT | Closed | Floor Tile | Restrooms | 2024-04-10 | 2024-04-12 | 2024-04-15 | 3 | Medium | TRUE | Material Defect | Medium | 45 | Initial batch rejected
T-1022 | PRJ001 | PRJ-MEP | Open | Fire Alarm Wiring | Level 2 | 2024-05-01 | 2024-05-10 |  |  | Medium | FALSE |  | Medium | 28 | Coordinating with electrician
T-1023 | PRJ001 | PRJ-ARC | Closed | Roof Membrane | Penthouse | 2024-02-20 | 2024-02-25 | 2024-02-24 | -1 | High | FALSE |  | High | 80 | Completed before deadline
T-1024 | PRJ001 | PRJ-SITE | Closed | Parking Lot Paving | North Lot | 2024-04-15 | 2024-04-20 | 2024-04-22 | 2 | Medium | TRUE | Asphalt Shortage | Medium | 60 | Truck delivery delay
T-1105 | PRJ001 | PRJ-STR | Closed | Post-Tensioning | Slab Area B2 | 2024-03-01 | 2024-03-05 | 2024-03-03 | -2 | High | FALSE |  | High | 105 | Optimal curing conditions
T-1106 | PRJ001 | PRJ-INT | Closed | Elevator Interior | Shaft 2 | 2024-04-05 | 2024-04-12 | 2024-04-15 | 3 | Medium | TRUE | Vendor Delay | Medium | 55 | Custom panels arrived late
T-1107 | PRJ001 | PRJ-MEP | Open | Fire Sprinklers | Level 7 | 2024-05-20 | 2024-06-01 |  |  | High | FALSE |  | High | 78 | Coordinating with steel deck
T-1108 | PRJ001 | PRJ-ARC | Closed | Stone Cladding | Entrance | 2024-02-15 | 2024-02-25 | 2024-03-05 | 8 | High | TRUE | Design Change | High | 115 | Revised architectural details
T-1109 | PRJ001 | PRJ-SITE | Closed | Fencing Installation | Security Zone | 2024-01-25 | 2024-02-01 | 2024-01-29 | -3 | Low | FALSE |  | Low | 42 | Early completion
T-1110 | PRJ001 | PRJ-STR | Closed | Metal Decking | Level 8 | 2024-03-10 | 2024-03-15 | 2024-03-20 | 5 | High | TRUE | Crew Shortage | High | 88 | Subcontractor staffing issue
T-1111 | PRJ001 | PRJ-INT | Open | Millwork Installation | Executive Suite | 2024-06-05 | 2024-06-15 |  |  | Medium | FALSE |  | Medium | 65 | Custom fabrication in progress
T-1112 | PRJ001 | PRJ-MEP | Closed | Electrical Terminations | Control Room | 2024-04-10 | 2024-04-15 | 2024-04-12 | -3 | Medium | FALSE |  | Medium | 48 | Completed ahead of schedule
T-1113 | PRJ001 | PRJ-ARC | Closed | Skylight Assembly | Atrium | 2024-03-05 | 2024-03-12 | 2024-03-18 | 6 | High | TRUE | Glass Breakage | High | 92 | Replacement unit required
T-1114 | PRJ001 | PRJ-SITE | Closed | Irrigation System | Landscape Area | 2024-02-01 | 2024-02-10 | 2024-02-15 | 5 | Low | TRUE | Utility Conflict | Medium | 50 | Required water line relocation
T-1001 | PRJ001 | PRJ-ARC | Closed | Foundation Pour | North Wing | 2024-01-05 | 2024-01-20 | 2024-01-22 | 2 | High | TRUE | Weather Delay | Medium | 120 | Concrete test passed
T-1002 | PRJ001 | PRJ-STR | Open | Steel Erection | East Tower | 2024-02-10 | 2024-03-15 |  |  | High | FALSE |  | High | 85 | Waiting for inspection
T-1003 | PRJ001 | PRJ-MEP | Closed | Electrical Rough-in | Level 5 | 2024-01-15 | 2024-02-01 | 2024-02-05 | 4 | Medium | TRUE | Supplier Delay | Medium | 65 | Completed with 3 RFIs
T-1004 | PRJ001 | PRJ-INT | Closed | Drywall Installation | Suite 401 | 2024-03-01 | 2024-03-10 | 2024-03-08 | -2 | Low | FALSE |  | Low | 42 | Early completion
T-1005 | PRJ001 | PRJ-SITE | Closed | Excavation | West Lot | 2024-01-10 | 2024-01-25 | 2024-01-30 | 5 | High | TRUE | Equipment Failure | High | 150 | Rock encounter required blasting
T-1006 | PRJ001 | PRJ-STR | Closed | Column Installation | Grid A5 | 2024-02-01 | 2024-02-05 | 2024-02-07 | 2 | High | TRUE | Crane Breakdown | High | 56 | Repaired after 1 day
T-1007 | PRJ001 | PRJ-INT | Open | Paint Finishes | Lobby | 2024-05-10 | 2024-05-20 |  |  | Medium | FALSE |  | Medium | 38 | Awaiting color approval
T-1008 | PRJ001 | PRJ-MEP | Closed | HVAC Ductwork | Mechanical | 2024-03-15 | 2024-03-22 | 2024-03-18 | -4 | Medium | FALSE |  | Low | 72 | Ahead of schedule
T-1009 | PRJ001 | PRJ-ARC | Closed | Curtain Wall Install | South Facade | 2024-04-01 | 2024-04-15 | 2024-04-20 | 5 | High | TRUE | Design Revision | High | 120 | Required engineering sign-off
T-1010 | PRJ001 | PRJ-SITE | Closed | Underground Utilities | West Yard | 2024-01-10 | 2024-01-25 | 2024-02-05 | 11 | High | TRUE | Weather Delay | Medium | 90 | Heavy rains for 1 week
T-1196 | PRJ001 | PRJ-INT | Closed | Floor Tile | Restrooms | 2024-04-10 | 2024-04-12 | 2024-04-15 | 3 | Medium | TRUE | Material Defect | Medium | 45 | Initial batch rejected
T-1197 | PRJ001 | PRJ-MEP | Open | Fire Alarm Wiring | Level 2 | 2024-05-01 | 2024-05-10 |  |  | Medium | FALSE |  | Medium | 28 | Coordinating with electrician
T-1198 | PRJ001 | PRJ-ARC | Closed | Roof Membrane | Penthouse | 2024-02-20 | 2024-02-25 | 2024-02-24 | -1 | High | FALSE |  | High | 80 | Completed before deadline
T-1199 | PRJ001 | PRJ-SITE | Closed | Parking Lot Paving | North Lot | 2024-04-15 | 2024-04-20 | 2024-04-22 | 2 | Medium | TRUE | Asphalt Shortage | Medium | 60 | Truck delivery delay
T-1200 | PRJ001 | PRJ-ARC | Open | Glass Curtain Wall | North Elevation | 2024-06-01 | 2024-06-15 |  |  | High | FALSE |  | High | 95 | Sequencing with steel work